## Milestone 1 Log
Stage | Date | Team Member | Action / Work Completed | Hours
Prep Stage | 14 May | Dylan | Researched and settled on the optimal applications, frameworks, and programming language (Python), considering the core features. | 2
Prep Stage | 14 May | An Jie | Developed and designed the poster and liftoff video; wrote the scripts. | 2
Prep Stage | 15 May | Both | Called with the advisor to discuss improvement pointers; revised large portions of the proposal and project based on the advice. | 1.5
Prep Stage | 16 May | Both | Filmed the liftoff video, finalised the poster, submitted on SkyLab, and finalised the core features and planning. | 1.5
Milestone 1 Work | 18 May | Both | Prepared and structured the codebase; created the local PostgreSQL database; set up Django to link with React and the local database. | 2
Milestone 1 Work | 19 May | Both | Set up the registration view and authentication routes; created the User serializer using the Django user model, plus the Profile model and serializer. | 3
Milestone 1 Work | 20 May | Both | Built the game engine (Tile, Hand, Deck, HandGenerator) with all tile types, discard and add_tile, deck build, shuffle and draw, and bonus replacement; created global auth state, the Axios JWT client, Login and Register forms, the protected home page, and React Router protected routes; wrote tests. | 6
Milestone 1 Work | 22 May | Both | Integrated the engine with Django REST Framework; created the random-hand endpoint (views.py, urls.py); built Home.jsx to fetch and display the 13-tile hand via Axios, with styling in index.css. | 3
Milestone 1 Work | 25 May | Both | Upgraded AuthContext to restore the JWT session on refresh; added the ProtectedRoute wrapper; built the AppLayout navigation shell. | 4
Milestone 1 Work | 27 May | Both | Created the profile serialization layer; built Profile.jsx; wrote frontend and backend test suites (10 tests); verified the production build with npm run build. | 5
Milestone 1 Work | 29 May | Both | Wrote the README documentation (architecture, JWT sequence, schemas, engine class diagram); cleaned the repository (removed venv, .env, and .DS_Store from git tracking). | 4
Milestone 1 Work | 30-31 May | Both | Poster design and video scripting. | 4

## Milestone 2 Log
Stage | Date | Team Member | Action / Work Completed | Hours
Milestone 2 Work | 1 Jun | Both | Planned the Milestone 2 scope and split the work into two parallel tracks (Trainer track and Tutorial track) to avoid merge conflicts. | 1.5
Milestone 2 Work | 1 Jun | Both | Set up feature branches and the pull request review workflow; created GitHub issues for the tasks. | 1.5
Milestone 2 Work | 2 Jun | An Jie | Implemented HandEvaluator strength scoring in engine.py (rewards complete sets, pairs, and near-sequences; penalises isolated tiles). | 3
Milestone 2 Work | 2 Jun | An Jie | Implemented ValuationAlgorithm.recommend_discard to evaluate all possible discards and return the best one with a reason. | 2.5
Milestone 2 Work | 3 Jun | An Jie | Created RecommendDiscardView with input validation (exactly 14 tiles, valid suits and values, max four copies) and routed /api/game/recommend-discard. | 2.5
Milestone 2 Work | 3 Jun | Dylan | Implemented the WinChecker engine class for standard hands, Seven Pairs, and Thirteen Orphans. | 4.5
Milestone 2 Work | 4 Jun | Dylan | Built the Hand Helper page (HandHelper.jsx) with a visual tile picker and the recommendation display. | 4.5
Milestone 2 Work | 4 Jun | Dylan | Built CheckWinView and routed /api/game/check-win; connected winning-hand detection for the Hand Helper. | 2.5
Milestone 2 Work | 5 Jun | Dylan | Wrote backend tests for HandEvaluator, ValuationAlgorithm, and the recommend-discard API. | 2.5
Milestone 2 Work | 5 Jun | Dylan | Wrote WinChecker and check-win API tests. | 2.5
Milestone 2 Work | 6 Jun | Dylan | Designed the TutorialProgress model with migration and admin registration. | 1.5
Milestone 2 Work | 7 Jun | Dylan | Built the tutorial serializers and the static module catalogue. | 1.5
Milestone 2 Work | 8 Jun | Dylan | Built the tutorial API (modules, progress, complete) with upsert on completion; routed the tutorial endpoints. | 3
Milestone 2 Work | 8 Jun | An Jie | Added the Session and Move models in the game app, with migration and admin registration. | 2.5
Milestone 2 Work | 9 Jun | An Jie | Built the Trainer API (trainer/new, trainer/submit, trainer/history) with discard scoring and move logging; routed the endpoints. | 4.5
Milestone 2 Work | 10 Jun | An Jie | Built the Trainer page (Trainer.jsx): deal a hand, pick a discard, show feedback and a running accuracy score; wired the route and nav link. | 4.5
Milestone 2 Work | 10 Jun | Dylan | Built the Tutorial page (Tutorial.jsx) with the module list and the lesson stepper. | 4.5
Milestone 2 Work | 11 Jun | An Jie | Wrote Trainer endpoint tests (auth, ownership, double-submit block, scoring, history). | 2.5
Milestone 2 Work | 11 Jun | Dylan | Created the TileCard, MeldDemo, and Quiz frontend components. | 4
Milestone 2 Work | 12 Jun | Dylan | Authored the lesson content and quizzes for the tile recognition, melds, and winning-hands modules. | 3
Milestone 2 Work | 12 Jun | Dylan | Wrote the tutorial backend tests; wired the tutorial route and nav link. | 2.5
Milestone 2 Work | 13 Jun | An Jie | Debugged the Trainer 500 error (duplicate sessions from get_or_create) and fixed it by selecting the most recent session. | 1.5
Milestone 2 Work | 13 Jun | An Jie | Diagnosed JWT token expiry and added an Axios refresh-and-retry interceptor. | 1.5
Milestone 2 Work | 14 Jun | Both | Reviewed and merged the feature branch pull requests; resolved merge conflicts. | 2.5
Milestone 2 Work | 15 Jun | An Jie | Implemented the points (tai) system: the SCORING table and ScoreCalculator (seat wind, round wind, dragons, seat flowers and animals, All Pongs, and flushes) with the minimum-one-tai rule. | 4.5
Milestone 2 Work | 16 Jun | An Jie | Added wind, dragon, and seat-flower position constants; built ScoreHandView and routed /api/game/score-hand. | 2.5
Milestone 2 Work | 18 Jun | An Jie | Implemented Kong logic: made WinChecker accept 14 to 18 tiles and treat Kongs as melds; added Hand.declare_kong and Deck.draw_replacement. | 4
Milestone 2 Work | 19 Jun | An Jie | Implemented claiming melds from discards: added the Meld class with a claimed flag and Hand.claim_pong, claim_chow, and claim_kong (exposed, locked melds). | 3
Milestone 2 Work | 20 Jun | Dylan | Built the reusable HandDisplay component (melds, concealed tiles, bonus row); wired it into Home and the Trainer; returned bonus tiles from the Trainer API. | 3
Milestone 2 Work | 21 Jun | An Jie | Wrote tests for the scoring system, kong wins, the kong redraw, and claimed melds. | 2.5
Milestone 2 Work | 23 Jun | An Jie | Built the Solo Play engine (solo.py): Player and SoloGame, dealing, the draw and discard loop, AI opponents using ValuationAlgorithm, flower replacement, concealed Kong, and the 16-tile washout reserve. | 6
Milestone 2 Work | 25 Jun | An Jie | Built the Solo Play API (solo/new, solo/state, solo/discard, solo/kong) with a per-user in-memory game store. | 3
Milestone 2 Work | 26 Jun | Dylan | Built the Solo Play page (SoloPlay.jsx): table view, hidden opponents, discard pile, clickable hand, and a kong action; wired the route and nav link. | 4.5
Milestone 2 Work | 26 Jun | Dylan | Wrote the Solo Play engine and API tests. | 2.5
Milestone 2 Work | 27 Jun | Dylan | Restyled the frontend to a plain, minimal theme (index.css). | 2.5
Milestone 2 Work | 28 Jun | Both | Manual end-to-end testing and bug triage across all features. | 2.5
Milestone 2 Work | 28 Jun | Both | Wrote the Milestone 2 README (architecture, data flow, and class diagrams; feature write-ups; bugs; software engineering practices). | 6
Milestone 2 Work | 29 Jun | Both | Compiled the Milestone 2 project log. | 1

## Hours Summary
Team member | Milestone 1 hours | Milestone 2 hours | Total hours
An Jie | 36 | 65.5 | 101.5
Dylan | 36 | 64 | 100
Total hours logged (all rows) | 38 | 114.5 | 152.5